## SOA
Zetas Zemin | [6 empty] | 2026-08-27
Statement of Account as of August 27, 2026
Invoice No | Invoice Date | Invoice Amount | Payment Date | Payment Amount | Balance | Description | Remarks
ZETDU-01151 | 2025-02-27 | 442050 | 2025-02-27 | 442050 | 0 | Enabling works design & early preparation works - PC01 - Stage 1A |  | 442050
ZETDU-01171 | 2025-03-30 | 884100 | 2025-06-19 | 842000 | 42100 | Enabling works design & early preparation works - PC02 - Stage 1A |  | 842000
ZETDU-01176 | 2025-04-29 | 1326150 | 2025-06-26 | 1263000 | 63150 | Enabling works design & early preparation works - PC03 - Stage 1A |  | 1263000
ZETDU-01189 | 2025-06-30 | 1768200 | 2025-07-01 | 1684000 | 84200 | Enabling works design & early preparation works - PC04 - Stage 1A |  | 1684000
ZETDU-01202 | 2025-07-15 | 17877954.675 | 2025-07-19 | 17026623.5 | 851331.175 | Enabling works design & early preparation works - PC05 - 10% of the contract - Stage 1B |  | 17026623.5
ZETDU-01203 | 2025-07-17 | 645750 | 2025-07-23 | 615000 | 30750 | Enabling works design & early preparation works - PC06 - Variation 01 |  | 615000
ZETDU-01221 | 2025-08-25 | 4522468.49 | 2025-08-28 | 4307112.8476 | 215355.6424 | Enabling works design & early preparation works - PC06 - Stage 1B |  | 4307112.8476
ZETDU-01243 | 2025-10-17 | 6416893.93 | 2025-11-26 | 6111326.6 | 305567.33 | Enabling works design & early preparation works - PC07 - Stage 1B |  | 6111326.6
ZETDU-01249 | 2025-11-03 | 10452758.19 | 2025-11-26 | 9955007.8 | 497750.39 | Enabling works design & early preparation works - PC08 - Stage 1B |  | 9955007.8
ZETDU-01263 | 2025-11-20 | 8372268.5 | 2025-12-19 | 7973589.05 | 398679.45 | Enabling works design & early preparation works - PC09 - Stage 1B |  | 7973589.05
ZETDU-01288 | 2025-12-17 | 2924079.9 | 2026-01-15 | 2784838 | 139241.9 | Enabling works design & early preparation works - PC10 - Stage 1B |  | 2784838
ZETDU-01294 | 2026-01-15 | 2210672.552 | 2026-02-04 | 2105402.4 | 105270.152 | Enabling works design & early preparation works - PC11 - Stage 1B |  | 2105402.4
ZETDU-01308 | 2026-02-16 | 6304870.79 | 2026-03-10 | 6004638.85 | 300231.94 | Enabling works design & early preparation works - PC12 - Stage 1B |  | 6004638.85
ZETDU-01325 | 2026-03-26 | 10367006.42 | 2026-04-10 | 9873339.45 | 493666.97 | Enabling works design & early preparation works - PC13 - Stage 1B |  | 9873339.45
ZETDU-01332 | 2026-04-27 | 4210319.28 | 2026-05-04 | 4009827.8857 | 200491.3943 | Enabling works design & early preparation works - PC14 - Stage 1B |  | 4009827.8857
ZETDU-01363 | 2026-06-02 | 8441929.17 | 2026-06-18 | 8039932.54 | 401996.63 | Enabling works design & early preparation works - PC15 - Stage 1B |  | 8039932.54
ZETDU-01365 | 2026-06-24 | 15987204.02 | 2026-07-27 | 3996801.01 | 11990403.01 | Enabling works design & early preparation works - PC16 - Stage 1B |  | 3996801.01
|  |  | 2026-07-31 | 11419431.44 | 570971.57 |  |  | 11419431.44
ZETDU-01371 | 2026-07-24 | 12236445.85 | 2026-08-13 | 11653757.9524 | 582687.8976 | Enabling works design & early preparation works - PC17 - Stage 1B |  | 11653757.9524
ZETDU-01382 | 2026-08-20 | 10801173.04 |  |  | 10801173.04 | Enabling works design & early preparation works - PC18 - Stage 1B |  |  | 10286831.4667 | 2571707.8667
Total - AED |  | 126192294.807 |  | 110107679.3257 | 16084615.4813 |  | -
% of Amount paid |  | 87.25%
[5 empty] | 4129782.9737 | Outstanding VAT Amount
[5 empty] | 3687732.9737 | Outstanding VAT Amount Less First Invoice
Payment Summary | [10 empty] | 1280682.77
Date | Amount | [9 empty] | 1282261
2025-02-27 | 442050 |  |  |  | 582687.8976
2025-06-19 | 842000 |  |  |  | 4700754.5437 | [5 empty] | -1578.23
2025-06-26 | 1263000 |  |  |  | 5283442.4413 |  |  | 98453921.3733 |  |  |  | 3.6456
2025-07-01 | 1684000
2025-07-19 | 17026623.5 |  |  | 11653757.9524
2025-07-23 | 615000 |  |  | 2913439.4881
2025-08-28 | 4307112.8476
2025-11-26 | 6111326.6
2025-11-26 | 9955007.8
2025-12-19 | 7973589.05
2026-01-15 | 2784838
2026-02-04 | 2105402.4
2026-03-10 | 6004638.85
2026-04-10 | 9873339.45
2026-05-04 | 4009827.8857
2026-06-18 | 8039932.54
2026-07-27 | 3996801.01
2026-07-31 | 11419431.44
2026-08-13 | 11653757.9524
Total - AED | 110107679.3257

## Summary
Zetas Zemin Teknologisi | [6 empty] | 2026-08-27
Statement of Account as of August 27, 2026
Scope | Contract value Inclu VAT | Amount Invoiced | Payment | Total Balance | Due Balance | Not Due | Paid % to Contract
Main Contract | 178779546.75 | 125546544.775 | 109492679.9257 | 69286866.8243 | 16053864.8493 | 53233001.975 | 61.24%
Variation | 645750 | 645750 | 615000 | 30750 | 30750 | 0 | 95.24%
Total | 179425296.75 | 126192294.775 | 110107679.9257 | 69317616.8243 | 16084614.8493 | 53233001.975
Summary_Main Contract |  |  |  |  | 69317616.8243 |  | 251425296.75 | Contract+Variation | 179425296.75
Phase | Contract Value Exclu. VAT | Payment Excluding VAT | Balance |  | 141317616.8243 |  | 115000000 | Addition | 71000000
Stage 1A | 4210000 | 4210000 | 0 |  |  |  | 53000000 | Total | 250425296.75
Stage 1B | 166056235 | 105261629.9257 | 60794605.0743 |  |  |  | 110107679.9257 | Paid | -110107679.9257
Total | 170266235 | 109471629.9257 | 60794605.0743 |  |  |  | -26682383.1757 | Receivables in 2026 | -113501473
[8 empty] | Escrow balance | -53137784.72
[8 empty] | Shortfall | -26321640.8957

## Main Contract
Zetas Zemin Teknologisi | [6 empty] | 2026-08-27
Statement of Account as of August 27, 2026
Particulars | Contract Value --AED-- | Vat 5% --AED-- | Total Value --AED-- | Amount Invoiced AED | Payment AED | Balance --AED-- |  | Amount AED | Narration | Date
Contract Value | 170266235 | 8513311.75 | 178779546.75
Stag 1A - Enabling works design & early prepation works - PC01 |  |  |  | 442050 | 442050 | 0 |  | 442050 | Funds transferred from ADCB LLC | 27.02.2025 | 421000
Stag 1A - Enabling works design & early prepation works - PC02 |  |  |  | 884100 | 842000 | 42100 |  | 842000 | Funds transferred from CBD Escrow | 19.06.2025 | 842000
Stag 1A - Enabling works design & early prepation works - PC03 |  |  |  | 1326150 | 1263000 | 63150 |  | 1263000 | Funds transferred from CBD Escrow | 26.06.2025 | 1263000
Stag 1A - Enabling works design & early prepation works - PC04 |  |  |  | 1768200 | 1684000 | 84200 |  | 1684000 | Funds transferred from CBD Escrow | 01.07.2025 | 1684000
Stag 1B - Enabling works design & early prepation works - PC05 - 10% |  |  |  | 17877954.675 | 17026623.5 | 851331.175 |  | 17026623.5 | Funds transferred from CBD Escrow | 19.07.2025
[6 empty] | 0 |  | 0 |  |  | 0%
[6 empty] | 0 |  | 0 |  |  | 0%
[6 empty] | 0 |  | 0 |  |  | 0%
[6 empty] | 0 |  | 0 |  |  | 0%
[6 empty] | 0 |  | 0 |  |  | 0%
[6 empty] | 0 |  | 0 |  |  | 0%
[6 empty] | 0 |  | 0 |  |  | 0%
Stag 1B - Enabling works design & early prepation works - PC06 |  |  |  | 4522468.49 | 4307112.8476 | 215355.6424 |  | 4307112.8476 | Funds transferred from CBD Escrow | 28.08.2025
Stag 1B - Enabling works design & early prepation works - PC07 |  |  |  | 6416893.93 | 6111327 | 305566.93 |  | 6111327 | Funds transferred from CBD Escrow | 26.11.2025
Stag 1B - Enabling works design & early prepation works - PC08 |  |  |  | 10452758.19 | 9955008 | 497750.19 |  | 9955008 | Funds transferred from CBD Escrow | 26.08.2025
Stag 1B - Enabling works design & early prepation works - PC09 |  |  |  | 8372268.5 | 7973589.05 | 398679.45 |  | 7973589.05 | Funds transferred from CBD Escrow | 19.12.2025
Stag 1B - Enabling works design & early prepation works - PC10 |  |  |  | 2924079.9 | 2784838 | 139241.9 |  | 2784838 | Funds transferred from CBD Escrow | 15.01.2026
Stag 1B - Enabling works design & early prepation works - PC11 |  |  |  | 2210672.52 | 2105402.4 | 105270.12 |  | 2105402.4 | Funds transferred from CBD Escrow | 04.02.2026
Stag 1B - Enabling works design & early prepation works - PC12 |  |  |  | 6304870.79 | 6004638.85 | 300231.94 |  | 6004638.85 | Funds transferred from CBD Escrow | 10.03.2026
Stag 1B - Enabling works design & early prepation works - PC13 |  |  |  | 10367006.42 | 9873339.45 | 493666.97 |  | 9873339.45 | Funds transferred from CBD Escrow | 04.02.2026
Stag 1B - Enabling works design & early prepation works - PC14 |  |  |  | 4210319.28 | 4009827.8857 | 200491.3943 |  | 4009827.8857 | Funds transferred from CBD Escrow | 04.05.2026
Stag 1B - Enabling works design & early prepation works - PC15 |  |  |  | 8441929.17 | 8039932.54 | 401996.63 |  | 8039932.54 | Funds transferred from CBD Escrow | 18.06.2026
Stag 1B - Enabling works design & early prepation works - PC16 |  |  |  | 15987204.02 | 15416232.45 | 570971.57 |  | 15416232.45 | Funds transferred from ADCB LLC & CBD Escrow | 27.07.2026 + 31.07.2026
Stag 1B - Enabling works design & early prepation works - PC17 |  |  |  | 12236445.85 | 11653757.9524 | 582687.8976 |  | 11653757.9524 | Funds transferred from CBD Escrow | 13.08.2026
Stag 1B - Enabling works design & early prepation works - PC18 |  |  |  | 10801173.04 |  | 10801173.04 |  | 0
Total | 170266235 | 8513311.75 | 178779546.75 | 125546544.775 | 109492679.9257 | 16053864.8493 |  | 109492679.9257

## Variations
Arup Gulf Limited | [7 empty] | 2026-07-28
Statement of Account as of July 28, 2026
Variation
Particulars | Contract Value --AED-- | Vat 5% --AED-- | Total Value --AED-- | Amount Invoiced | Invoiced % to Contract | Payment | Balance --AED-- |  | Amount AED | Payment Transferred From | Date
Variation 1: Sales Gallery - Shifting | 615000 | 30750 | 645750
Enabling works design & early prepation works - PC06 - Variation 01 |  |  |  | 645750 | 100% | 615000 | 30750 |  | 615000 | Funds transferred from CBD Escrow | 23.07.2025
25000
15000
7500
2500
Total Variation + Others | 615000 | 30750 | 645750 | 645750 | 100% | 615000 | 30750

## Sheet1
Zetas
Particular | Amount
Contract+Variation | 179425296.75
Addition | 71000000
Total | 250425296.75
Paid | -61114589.6476
Receivables in 2026 | -113501473
Escrow balance | -53137784.72
Shortfall | 22671449.3824

## 14.Nov.2024 (hidden)
Arup Gulf Limited | [5 empty] | 2024-11-14
Statement of Account as of November 14, 2024
Particulars | Contract Value --AED-- | Payment --AED-- | Balance --AED-- | Remarks | Notes
Contract Value - 20% of AED 2,546,250 | 509250 |  | 509250 | - | -
Transfer on 10-Jul-2023 against 20% Of Contract Value |  | 509250 | 0 | - | -
Contract Value - 20% of AED 2,546,250 | 509250 |  | 509250 | - | - | 509250 | Mobilisation
Transfer on 10-Jul-2023 against 20% Of Contract Value |  | 509250 | 0 | - | - | 135800.7 | End Jul, 2023 | Concept | Scheme | Digital Design | Total
Invoice No. 57-230079 - Dated 17-Aug-2023 | 135800.7 |  | 135800.7 | - | - | 135799.65 | End Aug, 2023 | 485000 | 970000 | 970000 | 2425000
Transfer on 28-Aug-2023 against Invoice No. 57-230079 |  | 135800.7 | 0 | - | - | 135799.65 | End Sep, 2023 | 24250 | 48500 | 48500 | 121250
Invoice No. 57-230090 - Dated 31-Aug-2023 | 135799.65 |  | 135799.65 | - | - | 203700 | End Oct, 2023 | 509250 | 1018500 | 1018500 | 2546250
Transfer on 27-Sep-2023 against Invoice No. 57-230090 |  | 135799.65 | 0 | - | - | 203700 | End Nov, 2023
Invoice No. 57-230106 - Dated 30-Sep-2023 | 135799.65 |  | 135799.65 | - | - | 203700 | End Dec, 2023
Transfer on 27-Nov-2023 against Invoice No. 57-230106 |  | 135799.65 | 0 | - | - | 203700 | End Jan, 2024
Invoice No. 57-230121 - Dated 31-Oct-2023 | 203700 |  | 203700 | - | - | 203700 | End Feb, 2024
Transfer on 11-Jan-2024 against Invoice No. 57-230121 |  | 203700 | 0 | - | - | 203700 | End Mar, 2024
Invoice No. 57-230143 - Dated 30-Nov-2023 | 203700 |  | 203700 | - | - | 203700 | End Apr, 2024
Transfer on 26-Jan-2024 against Invoice No. 57-230143 |  | 203700 | 0 | - | - | 203700 | End May, 2024
Invoice No. 57-230159 - Dated 31-Dec-2023 | 203700 |  | 203700 | - | - | 2546250 | -2037000
Transfer on 29-Feb-2024 against Invoice No. 57-230159 |  | 203700 | 0 | - | -
Invoice No. 57-230175 - Dated 31-Jan-2024 | 203700 |  | 203700 | - | -
Invoice No. 57-230195 - Dated 29-Feb-2024 | 203700 |  | 407400 | - | -
Invoice No. 57-230202 - Dated 18-Mar-2024 | 20328 |  | 427728 | - | -
Transfer on 28-Mar-2024 against Invoice No. 57-230175 |  | 203700 | 224028 | - | -
Transfer on 28-Mar-2024 against Invoice No. 57-230202 (SoundLab - 10% ) |  | 20328 | 203700 | - | -
Transfer on 28-Apr-2024 against Invoice No. 57-230195 |  | 203700 | 0 | - | -
Invoice No. 57-230215 - Dated 31-Mar-2024 | 203700 |  | 203700 | - | -
Transfer on 02-Jul-2024 against Invoice No. 57-230215 |  | 203700 | 0 | - | -
Invoice No. 57-240013 - Dated 30-Apr-2024 | 203700 |  | 203700 | Invoice 11: End April 24 as per agreed proposal dated on 21st June 2023 | -
Invoice No. 57-240028 - Dated 31-May-2024 | 498272.25 |  | 701972.25 | Invoice 12: End May 24 as per agreed proposal dated on 21st June 2023 - SoundLab - 50% on delivery of Phase 1 - VO2 Architectural Support - May 2024 | -
Invoice No. 57-240063 - Dated 30-Jun-2024 | 280628.25 |  | 982600.5 | VO2 Architectural Support - June 20242 - SoundLab - 40% on delivery of SoundLab presentation - Soundlab - Flight upgrade cost MAD-DXB for Stuart Clarke as instructed by Stuart Magee | -
Invoice No. 57-240085 - Dated 31-Jul-2024 | 487683 |  | 1470283.5 | VO2 Architectural Support - July 2024 - Invoice 13: End Jul 24 as per agreed proposal dated on 19 June 2024 - IAG review - mobilisation | -
Invoice No. 57-240101 - Dated 31-Aug-2024 | 390907.65 |  | 1861191.15 | VO3 Invoice 14: End Aug 24 Technical Advisory Services as per agreed proposal dated on 28 June 2024 - VO3 Architectural Support - August 2024 as per agreed proposal dated on 28 June 2024 - VO4 MEP Technical review of IAG project- 1st review as per agreed proposal dated on 19 June 2024 - VO5 Extension of Services – Fernando Garcia First trip on Aug 2024 as per agreed proposal dated on 16 July 2024 | -
Transfer on 22-Oct-2024 against Invoice No. 57-240013, 57-240028, 57-240063, 57-240101 |  | 976217 | 884974.15 |  | - | 982600.5 | 976216.5
Invoice No. 57-240116 - Dated 27-Sep-2024 | 477215.55 |  | 1362189.7 | Invoice 15: End Sep 24 as per agreed proposal dated on 19 June 2024 , VO3 Architectural Support - September2024 , VO5 Extension of Services – Fernando Garcia September 2024 | -
|  |  | 1362189.7 | - | -
Total | 5006834.7 | 3644645 | 1362189.7
% of Amount paid |  | 72.79%

## 13.Sep.2024 (hidden)
Arup Gulf Limited | [7 empty] | 2024-09-13
Statement of Account as of September 13, 2024
Particulars | Contract Value --AED-- | Payment --AED-- | Balance --AED-- | Balance --AED-- | Remarks | Description | Notes
Contract Value - 20% of AED 2,546,250 | 509250 |  | 509250 |  | - | - | -
Transfer on 10-Jul-2023 against 20% Of Contract Value |  | 509250 | 0 |  | - | - | -
Contract Value - 20% of AED 2,546,250 | 509250 |  | 509250 |  | - | - | -
Transfer on 10-Jul-2023 against 20% Of Contract Value |  | 509250 | 0 |  | - | - | -
Invoice No. 57-230079 - Dated 17-Aug-2023 | 135800.7 |  | 135800.7 |  | - | - | -
Transfer on 28-Aug-2023 against Invoice No. 57-230079 |  | 135800.7 | 0 |  | - | - | -
Invoice No. 57-230090 - Dated 31-Aug-2023 | 135799.65 |  | 135799.65 |  | - | - | -
Transfer on 27-Sep-2023 against Invoice No. 57-230090 |  | 135799.65 | 0 |  | - | - | -
Invoice No. 57-230106 - Dated 30-Sep-2023 | 135799.65 |  | 135799.65 |  | - | - | -
Transfer on 27-Nov-2023 against Invoice No. 57-230106 |  | 135799.65 | 0 |  | - | - | -
Invoice No. 57-230121 - Dated 31-Oct-2023 | 203700 |  | 203700 |  | - | - | -
Transfer on 11-Jan-2024 against Invoice No. 57-230121 |  | 203700 | 0 |  | - | - | -
Invoice No. 57-230143 - Dated 30-Nov-2023 | 203700 |  | 203700 |  | - | - | -
Transfer on 26-Jan-2024 against Invoice No. 57-230143 |  | 203700 | 0 |  | - | - | -
Invoice No. 57-230159 - Dated 31-Dec-2023 | 203700 |  | 203700 |  | - | - | -
Transfer on 29-Feb-2024 against Invoice No. 57-230159 |  | 203700 | 0 |  | - | - | -
Invoice No. 57-230175 - Dated 31-Jan-2024 | 203700 |  | 203700 |  | - | - | -
Invoice No. 57-230195 - Dated 29-Feb-2024 | 203700 |  | 407400 |  | - | - | -
Invoice No. 57-230202 - Dated 18-Mar-2024 | 20328 |  | 427728 |  | - | - | -
Transfer on 28-Mar-2024 against Invoice No. 57-230175 |  | 203700 | 224028 |  | - | - | -
Transfer on 28-Mar-2024 against Invoice No. 57-230202 (SoundLab - 10% ) |  | 20328 | 203700 |  | - | - | -
Transfer on 28-Apr-2024 against Invoice No. 57-230195 |  | 203700 | 0 |  | - | - | -
Invoice No. 57-230215 - Dated 31-Mar-2024 | 203700 |  | 203700 |  | - | - | -
Transfer on 02-Jul-2024 against Invoice No. 57-230215 |  | 203700 | 0 |  | - | - | -
Invoice No. 57-240013 - Dated 30-Apr-2024 | 203700 |  | 203700 |  | Invoice 11: End April 24 as per agreed proposal dated on 21st June 2023 | - | - |  | 203700
Invoice No. 57-240028 - Dated 31-May-2024 | 498272.25 |  | 701972.25 |  | Invoice 12: End May 24 as per agreed proposal dated on 21st June 2023 - SoundLab - 50% on delivery of Phase 1 - VO2 Architectural Support - May 2024 | - | - |  | 498272.25
Invoice No. 57-240063 - Dated 30-Jun-2024 | 280628.25 |  | 982600.5 |  | VO2 Architectural Support - June 20242 - SoundLab - 40% on delivery of SoundLab presentation - Soundlab - Flight upgrade cost MAD-DXB for Stuart Clarke as instructed by Stuart Magee | - | - |  | 274244.25
Invoice No. 57-240085 - Dated 31-Jul-2024 | 487683 |  | 1470283.5 |  | VO2 Architectural Support - July 2024 - Invoice 13: End Jul 24 as per agreed proposal dated on 19 June 2024 - IAG review - mobilisation | - | -
Invoice No. 57-240101 - Dated 31-Aug-2024 | 390907.65 |  | 1861191.15 |  | VO3 Invoice 14: End Aug 24 Technical Advisory Services as per agreed proposal dated on 28 June 2024 - VO3 Architectural Support - August 2024 as per agreed proposal dated on 28 June 2024 - VO4 MEP Technical review of IAG project- 1st review as per agreed proposal dated on 19 June 2024 - VO5 Extension of Services – Fernando Garcia First trip on Aug 2024 as per agreed proposal dated on 16 July 2024 | - | -
|  |  | 1861191.15 |  | - | - | -
Total | 4529619.15 | 2668428 | 1861191.15
% of Amount paid |  | 58.91%
[5 empty] | 509250 | Mobilisation
[5 empty] | 135800.7 | End Jul, 2023 | Concept | Scheme | Digital Design | Total
[5 empty] | 135799.65 | End Aug, 2023 | 485000 | 970000 | 970000 | 2425000
[5 empty] | 135799.65 | End Sep, 2023 | 24250 | 48500 | 48500 | 121250
[5 empty] | 203700 | End Oct, 2023 | 509250 | 1018500 | 1018500 | 2546250
[5 empty] | 203700 | End Nov, 2023
[5 empty] | 203700 | End Dec, 2023
[5 empty] | 203700 | End Jan, 2024
[5 empty] | 203700 | End Feb, 2024
[5 empty] | 203700 | End Mar, 2024
[5 empty] | 203700 | End Apr, 2024
[5 empty] | 203700 | End May, 2024
[5 empty] | 2546250 | -2037000

## 09.Jul.2024 (hidden)
Arup Gulf Limited |  |  |  |  | 2024-07-09
Statement of Account as of July 09, 2024
Particulars | Contract Value --AED-- | Payment --AED-- | Balance --AED--
Contract Value | 2546250 |  | 2546250
Transfer on Jul 10, 2023 against Inv ….. |  | 509250 | 2037000
Transfer on Aug 28, 2023 against Inv 57-230079 |  | 135800.75 | 1901199.25
Transfer on Sep 27, 2023 against Inv 57-230090 |  | 135799.65 | 1765399.6
Transfer on Nov 27, 2023 against Inv 57-230106 |  | 135799.65 | 1629599.95
Transfer on Jan 11, 2024 against Inv 57-230121 |  | 203700 | 1425899.95
Transfer on Jan 26, 2024 against Inv 57-230143 |  | 203700 | 1222199.95
Transfer on Feb 29, 2024 against Inv 57-230159 |  | 203700 | 1018499.95
Transfer on Mar 28, 2024 against Inv 57-230175 |  | 203700 | 814799.95
Transfer on Apr 28, 2024 against Inv 57-230195 |  | 203700 | 611099.95
Transfer on Jul 02, 2024 against Inv 57-230215 |  | 203700 | 407399.95
Total | 2546250 | 2138850.05 | 407399.95
% of Amount paid |  | 84%
|  |  |  | 509250 | Mobilisation
|  |  |  | 135800.7 | End Jul, 2023 | Concept | Scheme | Digital Design | Total
|  |  |  | 135799.65 | End Aug, 2023 | 485000 | 970000 | 970000 | 2425000
|  |  |  | 135799.65 | End Sep, 2023 | 24250 | 48500 | 48500 | 121250
|  |  |  | 203700 | End Oct, 2023 | 509250 | 1018500 | 1018500 | 2546250
|  |  |  | 203700 | End Nov, 2023
|  |  |  | 203700 | End Dec, 2023
|  |  |  | 203700 | End Jan, 2024
|  |  |  | 203700 | End Feb, 2024
|  |  |  | 203700 | End Mar, 2024
|  |  |  | 203700 | End Apr, 2024
|  |  |  | 203700 | End May, 2024
|  |  |  | 2546250 | 0

## 08.Jul.2024 (hidden)
Arup Gulf Limited |  |  |  | 2024-07-08
Statement of Accounts as of July 08, 2024
Particulars | Contract Value --AED-- | Payment --AED-- | Balance --AED--
Contract Value | 2546250 |  | 2546250
Transfer on Jul 10, 2023 against Inv ….. |  | 509250 | 2037000
Transfer on Aug 28, 2023 against Inv 57-230079 |  | 135800.7 | 1901199.3
Transfer on Sep 27, 2023 against Inv 57-230090 |  | 135799.65 | 1765399.65
Transfer on Nov 27, 2023 against Inv 57-230106 |  | 135799.65 | 1629600
Transfer on Jan 11, 2024 against Inv 57-230121 |  | 203700 | 1425900
Transfer on Jan 26, 2024 against Inv 57-230143 |  | 203700 | 1222200
Transfer on Feb 29, 2024 against Inv 57-230159 |  | 203700 | 1018500
Total | 2546250 | 1527750 | 1018500
% of Amount paid |  | 60%
[5 empty] | 509250 | Mobilisation
[5 empty] | 135800.7 | End Jul, 2023 | Concept | Scheme | Digital Design | Total
[5 empty] | 135799.65 | End Aug, 2023 | 485000 | 970000 | 970000 | 2425000
[5 empty] | 135799.65 | End Sep, 2023 | 24250 | 48500 | 48500 | 121250
[5 empty] | 203700 | End Oct, 2023 | 509250 | 1018500 | 1018500 | 2546250
[5 empty] | 203700 | End Nov, 2023
[5 empty] | 203700 | End Dec, 2023
[5 empty] | 203700 | End Jan, 2024
[5 empty] | 203700 | End Feb, 2024
[5 empty] | 203700 | End Mar, 2024
[5 empty] | 203700 | End Apr, 2024
[5 empty] | 203700 | End May, 2024
[5 empty] | 2546250 | 0

## 31.Dec.2023 (hidden)
Arup Gulf Limited
Statement of Accounts as of Dec 31, 2023
Particulars | Contract Value --AED-- | Payment --AED-- | Balance --AED--
Contract Value | 2546250 |  | 2546250
Transfer on Jul 10, 2023 against Inv ….. |  | 509250 | -509250
Transfer on Aug 28, 2023 against Inv 57-230079 |  | 135800.7 | -645050.7
Transfer on Sep 27, 2023 against Inv 57-230090 |  | 135799.65 | -780850.35
Transfer on Nov 27, 2023 against Inv 57-230106 |  | 135799.65 | -916650
Total | 2546250 | 916650 | 1629600
% of Amount paid |  | 36%

## Vendor List (hidden)
Vendor Name | CURRENCY | % PAID | CONTRACT VALUE | PAYMENT | BALANCE
Al Hai & Al Mukaddam for Geotechnical works LLC | AED | #REF! | #REF! | #REF! | #REF!
Al Tamimi & Company Ltd
Anta Travel & Tours
Arup Gulf Limited | AED | 60% | 2546250 | 1527750 | 1018500
Atelier One
BETC BNP | EUR | #REF! | #REF! | #REF! | #REF!
CBRE Dubai LLC | AED | #REF! | #REF! | #REF! | #REF!
Dezire Project Consultant
FALCON SURVEY ENGINEERING Consultants
Flint Culture MENA Marketing Management LLC
Korn/Ferry (Schweiz) GmbH
LuckyLion FZC-LLC | AED | #REF! | #REF! | #REF! | #REF!
Quali Consult Engineers | AED | #REF! | #REF! | #REF! | #REF!
March Made LLC | USD | #REF! | #REF! | #REF! | #REF!
Mazarine Middle East FZ-LLC | AED | #REF! | #REF! | #REF! | #REF!
Pentagram Design Limited | GBP | #REF! | #REF! | #REF! | #REF!
RCR Aranda Pigem Vilalta Arquitectes SLP | AED | #REF! | #REF! | #REF! | #REF!
Surface DMCC | AED | #REF! | #REF! | #REF! | #REF!
WSP Middle East Limited - Dubai Branch | AED | #REF! | #REF! | #REF! | #REF!